Annex 1.1.

GUIDELINES FOR THE SUCCESSFUL START OF PROJECT IMPLEMENTATION

TABLE OF CONTENTS

1. Study your Grant Contract thoroughly	4

2. Sign the Partnership Agreement	4

3. Allocate the Budget per Partners	4

4. Nominate the Project Team Members	5

5. Develop and use project monitoring tools	6

6. Prepare and plan for reporting	6

7. Develop communication channels	7

8. Create a systematic document filing system	8

9. Start early with procurement procedures	9

10. Use JTS support and be informed	9

11. Prepare a Project Communication and Visibility Plan	10

Annexes	12

Introduction

This document is designed to support beneficiaries through the initial stages of project implementation under the First Call for Proposals of the Programme. Its main purpose is to highlight the most important actions to be taken immediately after contract signature in order to ensure a smooth and efficient start of project implementation.

Successful project implementation relies on strong partnership, clear division of roles, and respect for the obligations defined in the Grant Contract. Each partner shares responsibility for the project, and cooperation must be based on mutual trust, transparency, and regular communication.

To support this process, model documents and templates are provided as annexes. These are intended to assist beneficiaries in setting up effective structures and tools for management, reporting, and compliance, while leaving room for adaptation to the specific needs of each partnership.

This document is organised into eleven concise sections (1–11). Each section contains good practices and points to model documents and templates provided in the Annexes, which should be adapted to the needs of each project and partnership.

Above all, early preparation, transparency and joint commitment are key to achieving the planned results and ensuring that the Action delivers long-term benefits to the cross-border community.

# Study your Grant Contract thoroughly

The Grant Contract you have signed contains important information on the requirements you need to respect during the project implementation. All partners and the whole project team need to understand those requirements. The Grant Contract consists of several annexes - it is complex and detailed. You are strongly advised to invest your time to study the Grant Contract properly. This will help you avoid difficulties later during the project implementation stage.

If you deviate from the requirements of the Grant Contract, this may have serious financial and/or legal consequences for the successful implementation of your project or even for your organization/institution.

It is particularly important to study the provisions of the Grant Contract at the very beginning of the project implementation. You not only need to be familiar with the applicable rules, but also with the time required to complete various procedures. Consulting your Grant Contract only after an issue has arisen is often too late for any corrective or remedy measures to be implemented in timely manner.

Good practices:

- Read the Grant Contract immediately after it is signed.

- Share key obligations and responsibilities with the entire project team.

- Mark important timelines and procedures directly in your internal calendar to ensure compliance.

# 1. Sign the Declaration on Ensuring the Sustainability of the Project

Within the first month of project implementation, the Coordinator shall sign the Declaration on Ensuring the Sustainability of the Project Annex 1.10, confirming its awareness of and commitment to comply with the sustainability obligations set out in the Grant Contract and the Programme rules.

All project partners shall undertake to comply with the same sustainability obligations through the Partnership Agreement Annex 1.3, which defines their respective responsibilities regarding the continued use, maintenance and preservation of the project results, outputs and assets throughout the sustainability period.

# 2. Sign the Partnership Agreement

All beneficiaries of the Grant Contract should sign a Partnership Agreement. A model template for the Partnership Agreement is provided in Annex 1.3 Any adjustments should be made only where necessary to reflect the specific arrangements agreed within the partnership.

The Partnership Agreement is an essential tool to ensure transparency, clarify roles, and build mutual commitment for the Action.

Good practices:

- Use Annex 1.3 as a starting point but adapt it to your partnership’s needs.

- Clearly define roles, responsibilities, and decision-making processes.

- Ensure all partners review and approve the final content of the Agreement.

- Keep a signed copy of the Partnership Agreement with all partners and the Coordinator.

# 3. Allocate the Budget per Partners

It is essential that budget allocations between partners are clearly defined and documented in a dedicated annex to the Partnership Agreement - Annex 1.4 Budget allocation between partners. Transparency in financial distribution is a key principle of EU-funded projects and ensures trust among all partners.

The Coordinator must also ensure that each partner is aware of their allocated budget, responsibilities for expenditure, and reporting obligations.

Good practices

- Share the agreed budget allocations with partners in writing (Annex 1.4).

- Ensure all partners clearly understand their financial responsibilities.

- Regularly review budget utilisation to avoid both overspending and underuse.

- Keep all budget allocations aligned with the Grant Contract.

# 4. Nominate the Project Team Members

One of the first implementation activities is the nomination of project team members. The template used for this purpose is Annex 1.2 – Decision on the establishment of the project team. This step ensures that responsibilities are assigned from the very beginning and that all key functions are covered.

Project beneficiaries must ensure that the internal project team members proposed in the approved project application are actively involved in project implementation, unless they are formally replaced in line with the established procedure and supported by an official Decision on the establishment of the project team (Annex 1.2).

Any replacement should respect the budgetary constraints and ensure that the newly appointed staff are equivalent in terms of qualifications, experience, and salary level.

Each partner should nominate competent staff members with clear roles, and the Coordinator must ensure that the team is balanced and capable of managing both technical and administrative aspects of the project. However, instead of each partner submitting a separate decision on the nomination of the project team, Annex 1.2 must be prepared and submitted by the Coordinator as a single consolidated document. This document should include the nominations of all staff members on behalf of the entire partnership and must be signed by the Coordinator. This approach ensures a unified, comprehensive overview of the complete project team.

In addition to submitting the Decision on the establishment of the project team (Annex 1.2), project partners must also provide a complete contact list of all project team members. This contact list, submitted as Annex 1.9 in accordance with the PIM, should be delivered at the start of the project and updated and re-submitted whenever changes occur during project implementation.

Good practices

- Nominate team members immediately after the contract signature.

- Ensure representation of each partner within the project team.

- Clearly define roles and responsibilities (administrative, financial, technical, communication).

- Keep the official nomination decision (Annex 1.2) properly filed and accessible.

# 5. Develop and use project monitoring tools

Development of monitoring tools is one of the key factors for efficient and successful project implementation. Such tools should be developed, systematically used, and integrated throughout the entire project implementation in order to support close tracking of the Action.

These monitoring tools are strongly recommended, as they help beneficiaries manage activities and finances more effectively; however, they are not obligatory, nor are they required to be submitted together with the regular reports.

Monitoring tools example templates are enclosed to this document:

- Annex 1.5 – Project Monitoring Tool provides a practical template for tracking project activities, responsibilities, timelines, and achievements, enabling beneficiaries to systematically monitor implementation progress and ensure accountability. It is recommended to monitor implementation monthly by regularly updating Annex 1.5.

- Annex 1.6 – Financial Monitoring Tool provides a template for tracking budget disbursement per budget line on a monthly basis.

The Coordinator should carry out financial monitoring of the grant budget on a regular, monthly basis to follow disbursement per budget line as indicated in the Grant Contract. This approach will help beneficiaries identify overspending early, as well as possible savings that can be re-allocated and further utilized.

All partners should actively use both Annex 1.5 and Annex 1.6 during project implementation to ensure consistent monitoring across the partnership and to facilitate timely and accurate reporting process by the Coordinator.

Please note:

- The pre-financing amount has been approved based on planned budget for the year 1 and it is expected that the planned activities and costs are realized during the first year of the project;

- Any delay in the implementation of activities must be communicated to the Contracting Authority/Intermediate Body for Financial Management.

Good practices:

- Use Annex 1.5 to track activities, responsibilities, and achievements on a monthly basis.

- Use Annex 1.6 to monitor financial flows against budget lines monthly.

- Share both tools among partners for transparency and consistency.

- Analyse monitoring data regularly to identify risks and implement corrective actions early.

- Document all deviations and adjustments clearly to support reporting and audit trails.

# 6. Prepare and plan for reporting

Reports are a cornerstone of project implementation, and the approval of your costs depends on their quality. Good reporting requires both careful planning and timely collection of supporting evidence.

First, review the official reporting templates. A good report can only be produced if you have all relevant information and supporting documentation at your disposal - on time. The process of drafting reports often raises questions about details that were not initially considered, so preparing early helps you to anticipate and resolve such issues.

It is strongly recommended to develop an internal reporting plan, allowing sufficient time for drafting, reviewing and finalising each report. The first report is especially important as it demonstrates your reporting capacities to the Contracting Authority/Intermediate Body for Financial Management.

Make sure that you closely follow the implementation of each activity and collect all supporting documentation, outputs, invoices, visibility materials etc.

It is strongly advised to start drafting your report in parallel with project implementation! This will help you capture important details accurately and verify your internal project plans regularly. A capable Coordinator ensures that the draft report is ready at least one to two weeks before the submission deadline, with all attachments included. This will allow Co-beneficiaries sufficient time to review and contribute, thereby improving both the content and the reporting process.

Detailed instructions on financial reporting and eligibility of costs are provided under Section 8. Reporting of the PIM.

Please pay attention to the deadlines of the Progress Report submission (Annex 3.1 of the PIM) according to the article 4.1.2 of the Special Conditions.

All partners must receive copies of the reports - narrative and financial - sent to the Contracting Authority/ Intermediate Body for Financial Management.

Good practices:

- Prepare an internal reporting schedule that aligns with official submission deadlines.

- Draft reports progressively during implementation, not only at the end of reporting period.

- Collect supporting documents (invoices, outputs, visibility materials) continuously.

- Share draft reports with co-beneficiaries at least two weeks before submission to ensure timely feedback and consistency.

# 7. Develop communication channels

Project implementation involves many people with different skills, responsibilities, priorities, interests, authority or other obligations, so it is the responsibility of the Coordinator to provide clear and timely instructions to ensure all stakeholders understand what is expected of them and to manage the continuous communication required for reports, timesheets, application of visibility rules, ensuring adequate proofs of the delivery of the activities, etc.

At the very beginning, establish clear communication channels, such as group emails, regular monthly meetings, shared calendars, and a single (digital) archiving space. These ensure timely coordination, prevent misunderstandings, and help partners stay aligned.

Just sending the project documents is NOT enough. People are rarely interested in reading complex documents especially in a foreign language. Use short summaries in English combined with direct communication. Schedule regular online or in-person meetings (via Zoom, Google Meet, Microsoft Teams, by phone, any mean of communication is better than lack of communication) and confirm that each individual/Grant beneficiary understands and commits to their tasks.

An introductory plenary meeting at the start of the project is strongly recommended. This meeting should define the responsibilities of each Grant beneficiary, build a sense of common interest, and highlight the interdependence and interconnectivity of all project activities. Any delay or missing input by one of Grant beneficiaries affects the whole project.

Since delays in activities or missing reports can jeopardize cost approval and the overall quality of reporting, it is essential that you, together with your team, provide detailed instructions from the start, gather information on partners’ procedures that may affect planning, and ensure that all aspects of the project are well understood and followed by everyone involved.

Good practices:

- Agree on a central communication channel (e.g. project email group).

- Schedule regular monthly meetings with fixed agendas.

- Share division of tasks and establish reporting routines from the start.

- Provide clear instructions and confirm that all partners understand timelines and reporting obligations.

# 8. Create a systematic document filing system

During the project lifetime, a large number of documents will be accumulated. Documents will keep on coming and very quickly you will have an issue finding them if they are not systematically filed. This can be avoided by preparing a clear filing system from the very beginning. This system should apply to both paper and digital project documentation and be organised according to project activities. It should also include one central digital archiving space accessible to the project team.

When it comes to financial documentation, it should be organised according to project budget lines.

Please note that the project is a subject to on-the-spot checks. For this grant scheme, the Department for Contracting and Financing of EU Funded Programmes (CFCU) of the Ministry of Finance of the Republic of Serbia as the Contracting Authority (CA)/Intermediate Body for Financial Management (IBFM), as well as the Control Body in North Macedonia is situated within the Department responsible for financial matters in the Ministry of Local Self-Government plan to execute on-the-spot checks/monitoring visits. They will examine your filing system and documentation – both financial and content related.

Besides on-the-spot-checks and monitoring visits, other checks may also take place during the implementation of the project or up to five years after the final payment to the project. Therefore, it is crucial that documents are always properly filed, so that everyone can easily understand the project status. Also, make sure that several project team members are familiar with the specific project filing system and can, therefore, provide the necessary data to any relevant check.

Good Practices:

- Set up the filing system at the very beginning of the project.

- Organize both paper and digital documents by project activities.

- Use one central digital archiving space accessible to the entire project team.

- Align financial documentation strictly with the approved project budget.

- Train multiple team members to manage and retrieve documents for internal and external checks.

# 9. Start early with procurement procedures

Procurement procedures for IPA-funded projects are among the demanding aspects for Grant beneficiaries, and this also applies to your project. Take this information very seriously now - it may save you considerable concerns later.

Each procurement (works, goods or services) under your project involves specific procedures that must be studied and correctly implemented. These procedures almost always take more time than expected. In addition, you may need to engage other relevant experts to support the procurement process, especially when purchasing equipment.

The Terms of Reference, Technical Specifications and Bills of Quantities have to be clear enough in order to allow potential competitors to offer what you need, but also for you to choose the best offer in line with clear selection and award criteria set in advance. Please bear in mind that potential providers of goods, services or works might be reluctant to participate in a process in which they must comply with unfamiliar rules, submit their offers in English language, and exclude VAT. They will probably have many questions and request explanations.

Furthermore, your tender documentation will almost automatically be reviewed by the Contracting Authority/Intermediate Body for Financial Management, especially in the case of larger amounts. This also take time. Therefore, make sure the Procurement Plan that you must submit at the beginning of the project implementation is realistic and allows sufficient time for possible delays.

Begin preparing procurement activities from the very first day of project implementation. Please consider this as one the most valuable pieces of advice, offered with the best intentions and based on substantial practical experience.

Good practices:

- Prepare the Procurement Plan immediately after the contract is signed.

- Anticipate delays - procurement procedures often take longer than expected.

- Engage technical experts when purchasing equipment, if deemed necessary.

- Draft clear and complete documentation, including Terms of Reference, Technical Specifications, and Bills of Quantities.

- Inform potential providers early about key requirements (e.g. English language, VAT excluded).

# 10. Use JTS support and be informed

The PIM provides detailed instructions and the necessary documents in addition to those annexed to the Call for Proposals. Make sure you study it thoroughly.

In addition, the Joint Technical Secretariat (JTS) team is available to provide support. On the webpage www.srb-bih.org you can find all the necessary information and contacts details, allowing you to request assistance and obtain clarification on questions related to the implementation of your project.

However, remember that it is your project to implement and the final responsibility lies with you while the JTS role is only advisory.

Finally, you will receive the contact details of the Project Manager at the Contracting Authority (CA)/Intermediate Body for Financial Management (IBFM) in charge of your project. You should contact this person only if absolutely necessary, as his/her primary task is not to provide support, but to ensure that your project is implemented in line with contractual obligations.

Good practices:

- Read the PIM carefully and use it as your main reference.

- Contact the JTS for practical advice and clarifications.

- Use the Programme webpage (www.srb-bih.org) as your primary information source.

- Contact the Project Manager at the Contracting Authority only when strictly necessary.

- Keep in mind that you are ultimately responsible for the successful project implementation.

# 11. Prepare a Project Communication and Visibility Plan

From the very beginning of project implementation, Grant beneficiaries must ensure that their project is visible to the wider public, with clear emphasis on the role of the European Union (EU) as the co-funding partner.

To achieve this, each beneficiary should prepare a Project Communication and Visibility Plan (Annex 1.7) covering the entire lifecycle of the project. All activities and materials must comply with the latest European Commission guidance – Communicating and Raising EU Visibility: Guidance for EU External Actions (2022). Practical instructions for implementation are available in Annex 6.2 – Guidelines on Implementing the Visibility Activities.

Grant beneficiaries must:

- Display the Programme logo, including the EU emblem and the correct funding statement (“Co-funded by the European Union”) on all project outputs, materials, equipment, publications, and events.

- Use the standard disclaimer on all communication materials:
“This publication/website/account/video/film/recording was co-funded by the European Union. Its contents are the sole responsibility of <name of the author/partner/project beneficiary> and do not necessarily reflect the views of the European Union.”

- Ensure all visibility elements are consistent, clear, and prominent across all channels and products.

#### Visibility is not just a contractual obligation — it is a communication tool that helps the public understand the project’s purpose, results, and the EU’s contribution. Effective visibility builds trust, increases awareness, and strengthens the impact of your project.

#### Good practices:

- Prepare the Communication and Visibility Plan at the very start of project implementation.

- Always use the Programme logo, including the EU emblem and the correct funding statement.

- Ensure visibility elements are consistent across all materials, events, and outputs.

- Consult the JTS or the CFCU/IBFM visibility officer for guidance if in doubt.

- Use creative approaches while fully respecting EU visibility rules.

- Make sure that local and cross-border target groups are well informed and engaged — they are the ultimate beneficiaries of project results.

# Annexes

- Annex 1.2 – Decision on the establishment of the project team

- Annex 1.3 – Model partnership agreement

- Annex 1.4 – Budget allocation between partners (Shared budget)

- Annex 1.5 – Project monitoring tool example

- Annex 1.6 – Financial monitoring tool example

- Annex 1.7 – Project Communication and Visibility plan

- Annex 1.8 – Procurement plan

- Annex 1.9 – Project team members contact list

- Annex 1.10 - Declaration on Ensuring the Sustainability of the Project

Documents to be submitted to the Contracting Authority (CA)/Intermediate Body for Financial Management (IBFM), following consultation with the JTS, within the first month after signing the contract:

- Decision on the establishment of the project team (Annex 1.2)

- Partnership Agreement (Annex 1.3)

- Budget allocation between partners (Shared budget) (Annex 1.4)

- Project Communication and Visibility Plan (Annex 1.7)

- Procurement Plan (Annex 1.8)

- Project team members contact list (Annex 1.9)

- Declaration on Ensuring the Sustainability of the Project (Annex 1.10)