## Reallocation
Re-allocation
Contract no: | Contract title: | [6 empty] | Reallocation No.1.date:
Expenses | Budget in contract or latest addendum |  |  |  | Reallocation No.1. |  |  |  | Variation € | Variation %
| Unit | # of units | Unit rate € | Costs € | Unit | # of units | Unit rate € | Costs €
1. Human Resources
1.1 Salaries (gross amounts, local staff)
1.1.1 Technical
1.1.1.1 Project manager | Per month | 12 | 700 | 8400 | Per month | 12 | 700 | 8400 | 0
1.1.1.2 Project coordinator (50% of full time) | Per month | 6 | 600 | 3600 | Per month | 6 | 600 | 3600 | 0
1.1.2 Administrative/ support staff
1.1.2.1 Accountant (50% of full time) | Per month | 6 | 600 | 3600 | Per month | 6 | 600 | 3600 | 0
1.2 Salaries (gross amounts, expat/int. staff)
1.2.1 Consultant in the field of EU policies (25% of full time) | Per month | 3 | 1200 | 3600 | Per month | 3 | 1200 | 3600 | 0
1.3 Per diems for missions/travel
1.3.1 Abroad (staff assigned to the Action)
1.3.1.1 Project manager | Per diem | 20 | 64 | 1280 | Per diem | 10 | 64 | 640 | -640 | -50%
1.3.2 Local (staff assigned to the Action)
1.3.2.1 Project manager | Per diem | 30 | 5 | 150 | Per diem | 30 | 5 | 150 | 0
1.3.3 Seminar/conference participants
1.3.3.1 Participants of seminar in Berlin | Per diem | 30 | 64 | 1920 | Per diem | 40 | 64 | 2560 | 640 | 33.33%
Subtotal Human Resources |  |  |  | 22550 |  |  |  | 22550 | 0
2. Travel
2.1. International travel
2.1.1 Airplane transportation | Per flight | 5 | 300 | 1500 | Per light | 4 | 300 | 1200 | -300 | -20%
2.2 Local transportation
2.2.1 Official vehicle transportation | Per km | 2500 | 0.22 | 550 | Per km | 2500 | 0.22 | 550 | 0
Subtotal Travel |  |  |  | 2050 |  |  |  | 1750 | -300 | -14.63%
3. Equipment and supplies
3.1 Furniture, computer equipment
3.1.1 Office work desk | Per item | 2 | 180 | 360 | Per item | 2 | 150 | 300 | -60 | -16.67%
3.1.2 Office work chair | Per item | 2 | 70 | 140 | Per item | 0 | 0 | 0 | -140 | -100%
3.1.3 Desktop computer | Per item | 2 | 450 | 900 | Per item | 1 | 450 | 450 | -450 | -50%
3.1.4 Laptop computer | Per item | 0 | 0 | 0 | Per item | 1 | 470 | 470 | 470
3.1.5 Printer | Per item | 0 | 0 | 0 | Per item | 1 | 180 | 180 | 180
Subtotal Equipment and supplies |  |  |  | 1400 |  |  |  | 1400 | 0 | 0%
4. Local office
4.1 Vehicle costs
4.1.1 Vehicle registration | Per vehicle | 1 | 350 | 350 | Per vehicle | 1 | 350 | 350 | 0
4.2 Consumables - office supplies | Per month | 12 | 45 | 540 | Per month | 12 | 45 | 540 | 0
4.3 Other services (tel/fax, electricity/heating, maintenance) | Per month | 12 | 90 | 1080 | Per month | 12 | 90 | 1080 | 0
Subtotal Local office |  |  |  | 1970 |  |  |  | 1970 | 0 | 0%
5. Other costs, services
5.1 Publications
5.1.1 Leaflet | Per copy | 1500 | 0.5 | 750 | Per copy | 1500 | 0.5 | 750 | 0
5.1.2 Brochure | Per copy | 1500 | 1.2 | 1800 | Per copy | 1500 | 1.2 | 1800 | 0
5.1.3 Poster | Per copy | 0 | 0 | 0 | Per copy | 300 | 1 | 300 | 300
5.2 Study on the Introduction of EU standards Into Business | Per study | 1 | 1500 | 1500 | Per study | 1 | 1500 | 1500 | 0
5.3 Translation, interpreters
5.3.1 Oral translation | Per hour | 20 | 50 | 1000 | Per hour | 20 | 50 | 1000 | 0
5.3.2 Written translation | Per page | 200 | 22 | 4400 | Per page | 200 | 22 | 4400 | 0
Subtotal Other costs, services |  |  |  | 9450 |  |  |  | 9750 | 300 | 3.175%
6. Other
6.1
Subtotal Other
7. Subtotal direct eligible costs of the Action (1-6) |  |  |  | 37420 |  |  |  | 37420 | 0 | 0%
8. Provision for contingency reserve (maximum 5% of 7, subtotal of direct eligible costs of the Action)
9. Total direct eligible costs of the Action (7+ 8) |  |  |  | 37420 |  |  |  | 37420 | 0 | 0%
10. Administrative costs (maximum 7% of 9, total direct eligible costs of the Action) | % | 2.35 | 37420 | 879.37 | % | 2.35 | 37420 | 879.37 | 0 | 0%
11. Total eligible costs (9+10) |  |  |  | 38299.37 |  |  |  | 38299.37 | 0 | 0%
Please mark with color the lines where re-allocations have been introduced.
new budget line
modified budget line
removed budget lines

## Justification of the Budget
Re-allocation
Justification of the Budget for the Action
Contract no: | Contract title: | [6 empty] | Reallocation No.1.date: |  |  | Clarification of a budget line | Justification of expenses estimation
Expenses | Budget in contract or latest addendum |  |  |  | Reallocation No.1. |  |  |  | Variation € | Variation % | Instruction: Explain why the expense related to budget re-allocation is necessary, e.g. how it contributes to the implementation of a specific activity. | Instruction: Explain how the cost was determined, e.g. based on market research or received offers.
| Unit | # of units | Unit rate € | Costs € | Unit | # of units | Unit rate € | Costs €
1. Human Resources
1.1 Salaries (gross amounts, local staff)
1.1.1 Technical
1.1.1.1 Project manager | Per month | 12 | 700 | 8400 | Per month | 12 | 700 | 8400 | 0
1.1.1.2 Project coordinator (50% of full time) | Per month | 6 | 600 | 3600 | Per month | 6 | 600 | 3600 | 0
1.1.2 Administrative/ support staff
1.1.2.1 Accountant (50% of full time) | Per month | 6 | 600 | 3600 | Per month | 6 | 600 | 3600 | 0
1.2 Salaries (gross amounts, expat/int. staff)
1.2.1 Consultant in the field of EU policies (25% of full time) | Per month | 3 | 1200 | 3600 | Per month | 3 | 1200 | 3600 | 0
1.3 Per diems for missions/travel
1.3.1 Abroad (staff assigned to the Action)
1.3.1.1 Project manager | Per diem | 20 | 64 | 1280 | Per diem | 10 | 64 | 640 | -640 | -50% | The number of per diem days for the Project Manager was reduced from 20 to 10 per diems because several coordination meetings (e.g. monthly meetings, Project Steering Committee Meetings) will be organised online rather than on-site. This adjustment reflects the updated implementation approach while maintaining the required level of project oversight. | The estimation is based on revised travel needs and updated scheduling, confirming that only 10 per diems are necessary for Project Manager for the travels planned until the end of project implementation. The per diem rate remains aligned with applicable rules and approved rates.
1.3.2 Local (staff assigned to the Action)
1.3.2.1 Project manager | Per diem | 30 | 5 | 150 | Per diem | 30 | 5 | 150 | 0
1.3.3 Seminar/conference participants
1.3.3.1 Participants of seminar in Berlin | Per diem | 30 | 64 | 1920 | Per diem | 40 | 64 | 2560 | 640 | 33.33% | The increase in the number of per diem units is due to the inclusion of additional participants from the beneficiary institution, following the involvement of another department in the implementation of Activity 1.3. Their attendance at the Berlin seminar is required to ensure that all staff involved are adequately trained and aligned with the project’s methodological and operational requirements and to ensure consistent application of the knowledge and methods introduced through the project. | The calculation is based on the confirmed list of seminar participants and the official per diem rate for Germany, as defined by national regulations. The estimated cost reflects actual attendance requirements.
Subtotal Human Resources |  |  |  | 22550 |  |  |  | 22550 | 0
2. Travel
2.1. International travel
2.1.1 Airplane transportation | Per flight | 5 | 300 | 1500 | Per light | 4 | 300 | 1200 | -300 | -20% | One planned international mission was cancelled due to a shift of the activity to an online format within Activity 1.1. Consequently, only four air trips are necessary to fulfil the project’s activity plan (Activity 1.4). | The number of tickets was recalculated according to the reduced number of required missions. Ticket cost estimation remain in line with the approved rates.
2.2 Local transportation
2.2.1 Official vehicle transportation | Per km | 2500 | 0.22 | 550 | Per km | 2500 | 0.22 | 550 | 0
Subtotal Travel |  |  |  | 2050 |  |  |  | 1750 | -300 | -14.63%
3. Equipment and supplies
3.1 Furniture, computer equipment
3.1.1 Office work desk | Per item | 2 | 180 | 360 | Per item | 2 | 150 | 300 | -60 | -16.67% | The total number of 2 desks remain necessary to equip the project office and provide adequate workspace for staff involved in implementation and reporting tasks (Activity 1.6). | Recent market research identified more economical suppliers offering comparable quality desks at 150 EUR per unit. The revised amount reflects actual market conditions and ensures cost-efficient spending.
3.1.2 Office work chair | Per item | 2 | 70 | 140 | Per item | 0 | 0 | 0 | -140 | -100% | This item was removed because the project office already has sufficient chairs available, and additional units are no longer required for implementing project activities.
3.1.3 Desktop computer | Per item | 2 | 450 | 900 | Per item | 1 | 450 | 450 | -450 | -50% | The number of desktop computers is reduced from 2 to 1 because project staff will increasingly perform field-based and mobile tasks within related Activity 1.2. As a result, a second desktop unit is no longer needed, since stationary equipment is less suitable for the updated implementation workflow. | The number of desktop computers was recalculated according to the actual needs within Activity 1.2. Desktop computer cost estimation remain in line with the approved rates.
3.1.4 Laptop computer | Per item | 0 | 0 | 0 | Per item | 1 | 470 | 470 | 470 |  | Due to the increased need for fieldwork, on-site data collection and mobility within Activity 1.2., a laptop is required to ensure that project staff can perform tasks outside the office efficiently. A portable device provides greater flexibility than a second desktop computer. | The cost estimation is based on market research of mid-range laptops suitable for professional use, including quotations from local suppliers and online market comparisons. The selected amount represents the most economical equipment item meeting the technical specification requirements.
3.1.5 Printer | Per item | 0 | 0 | 0 | Per item | 1 | 180 | 180 | 180 |  | A printer is necessary to ensure timely production of project documentation, visibility materials and administrative records required for monitoring, reporting and on-site implementation. Given the increased volume of documents generated during field activities and coordination events within Activities 1.2. and 1.5., having a multifunctional printer available enables efficient preparation of forms, attendance sheets, visibility outputs and supporting evidence needed for audits and compliance with applicable programme rules. | The cost estimate is based on a review of prices for standard multifunctional printer (printing, scanning, copying) offered by several local suppliers. The selected price corresponds to the lowest available market rate for the equipment item meeting the technical needs of the project.
Subtotal Equipment and supplies |  |  |  | 1400 |  |  |  | 1400 | 0 | 0%
4. Local office
4.1 Vehicle costs
4.1.1 Vehicle registration | Per vehicle | 1 | 350 | 350 | Per vehicle | 1 | 350 | 350 | 0
4.2 Consumables - office supplies | Per month | 12 | 45 | 540 | Per month | 12 | 45 | 540 | 0
4.3 Other services (tel/fax, electricity/heating, maintenance) | Per month | 12 | 90 | 1080 | Per month | 12 | 90 | 1080 | 0
Subtotal Local office |  |  |  | 1970 |  |  |  | 1970 | 0 | 0%
5. Other costs, services
5.1 Publications
5.1.1 Leaflet | Per copy | 1500 | 0.5 | 750 | Per copy | 1500 | 0.5 | 750 | 0
5.1.2 Brochure | Per copy | 1500 | 1.2 | 1800 | Per copy | 1500 | 1.2 | 1800 | 0
5.1.3 Poster | Per copy | 0 | 0 | 0 | Per copy | 300 | 1 | 300 | 300 |  | The poster is required to ensure project visibility during field activities, stakeholder meetings and events conducted outside the project office. As mobility and on-site engagement have increased, having a high-quality, durable and portable poster as a visibility tool suitable for repeated use throughout the project’s implementation period to meet progarmme visibility rules and to properly communicate project objectives to participants and local stakeholders. | The price is based on quotations for premium, reusable visibility materials from specialised printing providers. The cost estimate reflects the most economical option fulfilling visibility requirements.
5.2 Study on the Introduction of EU standards Into Business | Per study | 1 | 1500 | 1500 | Per study | 1 | 1500 | 1500 | 0
5.3 Translation, interpreters
5.3.1 Oral translation | Per hour | 20 | 50 | 1000 | Per hour | 20 | 50 | 1000 | 0
5.3.2 Written translation | Per page | 200 | 22 | 4400 | Per page | 200 | 22 | 4400 | 0
Subtotal Other costs, services |  |  |  | 9450 |  |  |  | 9750 | 300 | 3.175%
6. Other
6.1
Subtotal Other
7. Subtotal direct eligible costs of the Action (1-6) |  |  |  | 37420 |  |  |  | 37420 | 0 | 0%
8. Provision for contingency reserve (maximum 5% of 7, subtotal of direct eligible costs of the Action)
9. Total direct eligible costs of the Action (7+ 8) |  |  |  | 37420 |  |  |  | 37420 | 0 | 0%
10. Administrative costs (maximum 7% of 9, total direct eligible costs of the Action) | % | 2.35 | 37420 | 879.37 | % | 2.35 | 37420 | 879.37 | 0 | 0%
11. Total eligible costs (9+10) |  |  |  | 38299.37 |  |  |  | 38299.37 | 0 | 0%
Please fill in only those budget lines where there have been budget re-allocations clearly justiying the re-allocation.
new budget line
modified budget line
removed budget lines