# Please insert requested information in brackets, and remove brackets and highlights before printing.

# Note: This area will not print.

< Letterhead of the Beneficiary >

Request for an Addendum

[Head of CA/IBFM]

< Date>

RE:	Request for Addendum No. 1 <insert consecutive number of the Request for Addendum>

Purpose of Addendum: Reallocation between budget headings exceeding 25%/ No-cost extension of the project implementation period

Contract No:

Grant Amount EUR:

Title of Project:

Dear Mr./Ms ………,

In accordance with the Article 9- Amendment of the contract of the General Conditions, we would like to request your approval for the following modifications to the above-mentioned contract:

Major budget modification

WHAT WILL CHANGE:

An amount of EUR 600 will be reallocated from Budget Heading 2. Travel (budget line 2.1.1 Airplane transportation) to newly introduced budget line 3.1.6 Projector in Budget Heading 3. Equipment and supplies. The reallocation exceeds the 25% limit foreseen by the Grant Contract.

WHY IT WILL CHANGE:

The reallocation is required due to reduced travel needs, as one planned international mission under Activity 1.4 was cancelled following the shift of the activity to an online format. As a result, only two airline transportation trips are necessary in total to implement Activity 1.4, generating a saving within Budget Heading 2 Travel. These available funds will be reallocated to cover the cost of a high-quality, lightweight, easy to transport, portable projector under Budget Heading 3. Equipment and supplies. The portable smart projector is required to support the implementation of project activities that involve fieldwork, stakeholder engagement, capacity-building sessions and visibility events conducted outside the main project office (Activities 1.2. - Activity 1.6.).

The table below summarizes the major budget amendments:

| Budget Heading /Budget Item | Initial contract budget |  |  |  | Amendment |  | Amended Budget |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel | Unit | # of units | Unit rate (EUR) | Costs (EUR) | EUR | % of Budget heading | # of units | Unit rate (in EUR) | Costs (in EUR) |
| 2.1.1 Airplane transportation | Per flight | 5 | 300,00 | 1.500,00 | -900,00 | -43,90% | 2 | 300,00 | 600,00 |
| 5. Other costs, services |  |  |  |  |  |  |  |  |  |
| 3.1.6 Projector | Per item | 0 | 0 | 0 | 600,00 | 42,86% | 1 | 600,00 | 600,00 |

Following supporting documents are attached: market research for lightweight, easy to transport, portable projector (budget line 3.1.6. Projector)

No cost extension of the project implementation period

WHAT WILL CHANGE:

The project implementation period will be extended without any increase in the approved project budget. In line with the Implementing Manual, a modified Annex I – Description of the Action is submitted in both track changes and clean versions. The modification of the project duration is reflected in:

- the narrative part of Annex I, where the duration of activities is described, and

- the Indicative Action Plan, which has been updated accordingly.

WHY IT WILL CHANGE:

The requested no-cost extension is required due to delays affecting the implementation of certain project activities. These delays are duly justified in the revised Annex I, which clearly specifies:

- the activities implemented to date,

- the reasons for the delay for each affected activity, and

- the parts of the activities planned for implementation during the extended period.

The requested extension will allow for the full and proper completion of the planned activities and achievement of project objectives, while ensuring compliance with the Grant Contract and the Implementing Manual. The extension does not entail any changes to the approved budget.

Following documents are attached:

- Modified Annex I – Description of the Action (track changes and clean versions)

We kindly ask you to review the request and inform us should any additional information or clarification is required.

Yours Sincerely,

<Signature of authorised representative of the legal entity >

< Name and position of authorised representative of the legal entity >