Addendum modifying the budget:

The Coordinator prepares and sends to JTS:

1.draft Request for Addendum (Annex 2.3) with thorough justification,

2.Budget Reallocation Table (Annex 2.2)

3. Revised Annex III (Budget

4.relevant supporting documentation, and

5. updated Annex I (if applicable)

Addendum not modifying the budget:

The Coordinator prepares and sends to JTS:

1.draft Request for Addendum (Annex 2.3) with thorough justification,

2.relevant supporting documentation, and

3. updated Annex I (if applicable)

Major modification infographic

Consultation with JTS:

The JTS reviews the draft documents and, if applicable, advises necessary adjustments.

Finalization of documents:

The Coordinator prepares final Request for Addendum and the relevant supporting documentation, signs and stamps it and sends it to the CA/IBFM via email and hard copy via post, at least 30 days/preferably 40 days before the major modification is intended to enter into force. Sends it via email to JTS as well.

Review and approval:

CA/IBFM reviews submitted Request for Addendum with supporting documentation. Upon internal control within the CA/IBFM and ex-ante approval by the EUD, three copies of the Addendum are submitted to the Coordinator for countersignature.