## Annex 5.5. - Guidance for procurement through Single Tender and Simplified procedures

## This document serves as a step-by-step guidance instruction on how to use and complete all procurement documentation provided within Annex 5 “Secondary Procurement”.

- SINGLE TENDER PROCEDURE

Contracts for services, supplies or works with a value of less than or equal to EUR 20,000 may be awarded under the single tender procedure.

In the single tender procedure, only one tenderer may be invited to submit a formal offer. However, it is recommended to contact more than one potential tenderer (preferably three) to compare current market prices and to ensure the best quality-price ratio.

The list of documents that must be prepared under the single tender procedure and provided ex-post (after completion of the procurement procedure) to the CA/IBFM and Control body for the verification purposes is the following:

Procurement planning, market research and tender preparation:

- Procurement plan (Annex 1.8. Project setup)

- Market Research for suply contract – example (Annex 5.1. Tender preparation)

- Market Research and Justification for Tender Invitation (Annex 5.2. Single Tender Dossier)

- Declaration of Objectivity and Confidentiality (Annex 5.1. Tender preparation)

- Invitation letter (Annex 5.2. Single Tender Dossier)

- Tender Dossier - consisting of the following documents:

- PART A – Information for the tenderers (Terms of Reference/Technical Specifications/Bill of Quantities, Draft Contract, Administrative Grid, Evaluation Grid; CV template, Statement of Exclusivity and Availability template)

- PART B – Format of offer to be provided by the tenderer (templates for submission of the technical offer

- PART C – Financial offer

- Evaluation report template

Tender launch

- Evidence of invitations to submit tenders sent

- Evidence of offers received

Tender evaluation (Annexes 5.3):

- Decision on the appointment of the Evaluation Committee

- Declaration of absence of conflict of interest and of confidentiality (Evaluation Committee members)

- Register of tenders received

- Acknowledgment of receipt of tenders

- Tender opening checklist & report

- Administrative compliance grids

- Technical evaluation grids

- Clarification correspondence, if applicable

- Evaluation report

- PRAG Evaluation report (ex Negotiation report)

Contract award:

- Contract award notification letter

- Letters to unsuccessful tenderers

- Cancellation notice, if applicable

Contract implementation:

- Timesheets for service contracts, where applicable;

- Service provider reports evidencing completion of the services;

- Provisional/Final Acceptance Certificates for supply and works contracts.

Single tender procedures should follow the procurement steps described below:

### Step 1 – Procurement planning

Related annex: Annex 1.8

Procurement planning includes deciding which procedure will be used, setting the timeframe for launching tenders, and conducting a market analysis. All planned procurements must be consistent with the Description of Action (Annex I) and Grant Budget (Annex III).

The Coordinator must prepare a Procurement Plan (PP) and submit it first to the JTS for consultation and then officially to the CFCU within the first month from the start of contract implementation, using the template provided in Annex 1.8.

The CFCU Project Manager (PM) plays a key role in the preparation and approval of the Procurement Plan. The PP is reviewed jointly by the JTS and the CFCU PM, who checks that the PP is consistent with the approved Budget and the Shared Budget. If and when necessary, the CFCU PM also coordinates with the Control Body (CB) and integrates their opinion into the review process.

Any changes to the Procurement Plan must immediately be communicated to the JTS and CFCU PM.

Following the review of the Procurement Plan, the CFCU PM will notify the Coordinator and confirm by e-mail when there are no further comments, with the review and approval to be completed within 15 working days from the submission of the PP.

### Step 2 – Market research

Related annexes: Annexes 5.1.

In order to prepare the single tender procedure, and to comply with the principles of sound financial management, of the effectiveness and the efficient use of public funds, it is recommended that the Grant Beneficiaries conduct preliminary market research/assessment/consultation prior to the formal launch of a single tender procedure. This may consist of one or a combination of the following:

- pro-forma offers,

- reference prices obtained through online price lists or centralised e-procurement services,

- other methods, as appropriate.

The market research may follow the “three-reference prices” principle, meaning that the Grant Beneficiaries should obtain at least three comparable references containing the following parameters:

- description of technical specifications / terms of reference,

- quantities,

- expertise,

- price,

- other relevant characteristics of the subject matter of procurement, if applicable (e.g. delivery/implementation/performance period, types and duration of guarantees, payment options, and other conditions of contract implementation).

The purpose of the market research is to examine price, quantity, quality, delivery period, rule of origin and other important criteria, as it will be set out in the tender dossiers.

For the purpose of documenting their market research, Grant beneficiaries shall prepare market research table summarising the outcome of the market assessment. The table should include each service/supply/works item to be procured, a list of possible suppliers, country of origin, copies of technical documentation or offers (as attachments), and the estimated prices obtained. Based on the comparison of offers, the ‘relevant price’ for each item is selected and recorded. Finally, a summary price estimation is provided at the end of the table, showing the total estimated cost of all items/lots/supplies/services/works. The example of such a table is available as Annex 5.1. (01 Market research for supply contract – example) to this document.

The market research table should serve as an input for drafting “Market assessment and justification of the selected companies for tender invitation” – please see examples within Annex 5.2 - documents 01a and 01b “Market Assessment and Justification”. In addition to the market research table, this Annex must also include a strong justification of the choice of invited tenderers, based on market research and objective criteria used to determine which tenderers are invited to submit offers. For easier reference, the template also contains an example.

### Step 3 – Tender Dossier preparation

### arket research

Related annexes: Annexes 5.1. (01-05), Annexes 5.2 (01-04)

Following the market research, Grant beneficiaries need to prepare the Tender Dossier to launch the single tender procedure.

It is strongly recommended that Grant Beneficiaries seek support from JTS/AO during the preparation of the tender documentation, before procedure is formally launched.

For single tender procedure, it is envisaged to use the single Tender Dossiers in Annex 5.2. The Tender Dossier must contain all necessary terms and information to enable the tenderers to adequately prepare their offers. It shall specify the procedures to be followed when applying for a tender, the required documentation to be submitted, as well as the place and deadline for submission. It must also clearly state the selection criteria, award criteria, evaluation criteria, contractual obligations, delivery conditions, guarantees, payment options, and any other requirements relevant for contract implementation.

In general, tender documentation for single tender procedures for services, supplies, and works consists of:

- Part A – Information for the tenderer: Instructions to Tenderers (ITT), Terms of Reference/Technical Specifications, Bill of Quantities (BoQ), Draft Contract, Administrative Grid, Evaluation Grid;

- Part B – Format of offer to be provided by the tenderer (templates for submission of the technical offer);

- Part C – Financial offer.

Any part of tender documentation, particularly the Terms of Reference, Technical Specifications, or BoQ, must not be disclosed to any third party and must remain confidential until made available to all tenderers simultaneously. All participants in the preparation process must sign a Declaration absence of conflict of interest and of confidentiality (Annex 5.3 point 06).

  - Document: Part A – Information for the tenderer:

This document should provide potential tenderer(s) with clear information regarding procedural requirements and description of service/supply/works to be purchased.

Legal entities are entitled to participate in all types of procedures, while natural persons may take participation only in service contracts.

### Instructions for the section of the document: 1. INFORMATION ON SUBMISSION OF THE TENDERS

Subject of the contract

For SERVICE / SUPPLY / WORKS:

Deadline for submission of the tenders

The potential tenderer(s) should be given minimum 7 days from the date of launching of the procurement procedure for preparation and submission of the offer (excluding the day of publishing and the date of submission deadline) in case of service and supply contract, and minimum 10 days in case of works contracts.

These time limits cannot be shortened; however, the Contracting Authority is encouraged to consider allowing a longer period, depending on the nature and subject of the contract, or in cases of larger or more complex procurements.

Concerning the works contracts, a site visit may be held during this period. The date, the time and the venue of the site visit should be stated; therefore, the timeframe for submission of offer(s) should be set accordingly.

Financial information – for SERVICE:

This section is applicable only for service contracts. The maximum budget available for the contract should be specified here. Sometimes this will require combining of several budget lines from the Grant Budget (Annex III). The maximum budget available for the contract may be stated in national currency or in EUR.  The exchange rate to be used for conversion shall be InforEuro exchange rate for the month when the tender is launched.

Currency – for SUPPLY / WORKS:

For supply and works contracts, no price indications are allowed. Grant Beneficiaries must also bear in mind the rule of origin when applicable to supply and works contracts.

Award criteria – SERVICE

In case of service contracts, award criteria depend on the number of offers to be evaluated, as follows:

- In case  one offer is received, only administrative, technical and financial compliance with the requirements set by tender documentation will be checked.

- In  case  more than one offer is received, award criterion is the best price–quality ratio, weighting 80% technical quality and 20% price. The calculation method is explained in PRAG 2025 Manual under section 3.4.10.3. Evaluation of offers.

Award criteria – SUPPLY / WORKS

In case of supply and work contracts, the award criterion is the lowest price of technically compliant offer.

Submission of the tenders

The tenderers will submit their tenders using the standard set of submission forms available in the Part B – Technical offer and the Part C - Financial offer.

Technical offer of the tender should fulfil minimum technical requirements as set out section 2. Technical information of the PART A – Information for the tenderers.

Technical offer template depends on the type of contract: for service contract, it is Organisation and methodology, proposed inputs by the tenderer, proposed time frame, for the supply and works it is Technical specification form/bill of quantities.

In case of key experts, CV and Statement on availability and exclusivity should be provided by the tenderers in their offers.

In case the tender is divided into lots, a separate tender submission form must be delivered by the tenderer.

### Instructions for the section of the document: 2. TECHNICAL INFORMATION

Grant Beneficiaries should pay special attention when formulating relevant technical information since it is the precondition for receiving the offers with the appropriate quality and for successful implementation of the contract.

SERVICE

Relevant technical requirements for service contract should be formulated under section “Technical information” providing the detailed information on the scope, activities, expected results of the service contract, as well as the required expertise of the experts (as in the Terms of Reference).

Title of activities should be concise and clear, describing in short, the main purpose of services to be provided. An activity should combine all tasks related to the same activity (such as events, promotion, expertise…) in line with the approved Description of the Action (Annex I). Usually, tasks within one activity require engagement of the same or similar inputs and resources necessary for their implementation (such as staff, premises, equipment, material…). Specification of expected outputs / results to be achieved should be presented in accordance with description of activities as per the DoA and need to comply with normal market standards for similar type of services.

The description of expected outputs, required inputs and timeframe should be clearly defined and described in sufficient details.

To verify required inputs, it is recommended to request submission of relevant CVs for assessment. This ensures that the appropriate expertise is secured for service delivery, with experts evaluated against the requirements set out under the section “Required inputs”.

If the outputs of the requested services are tangible, such as catering for xx people, overnight stay for xx training participants, development study or research, xx leaflets or brochures, created web site etc., global price service contract should be used with the relevant tender documentation.

If the outputs are not easily predicable, such as hiring a company that will provide a group of experts for training, monitoring of procedures, fee-based service contract should be used with the relevant tender documentation.

In the case of fee-based service contracts, the qualifications, skills, and both general and specific experience for the experts must be clearly defined while avoiding overly restrictive criteria.

It is recommended to request reports from external service providers in order to account for the expenditure incurred and to demonstrate progress in the delivery of outputs.

Information on how the offers will be evaluated must also be provided to potential tenderers. In this regards, Grant Beneficiary must indicate the maximum number of points to be assigned for Organization and Methodology, Required inputs and Timeframe in the Evaluation Report.

SUPPLY

Technical specifications should be precise and detailed, comprising minimum technical requirements and quantities, but not restrictive in description, targeting, favouring or excluding a specific product. Mentioning brand names (or specific model of any brand) should be avoided. If name of a certain brand or producer/supplier cannot be avoided, this reference should be followed by the expression "or equivalent" or should be used with expression “to be compatible with….”. Any additional requirements, such as: (commercial) warranty, delivery, installation, training, testing, generally accepted standards, visibility requirements, maintenance…) should be precisely stated.

When drafting Technical specifications, the information obtained during market research phase should be used as the basis, especially concerning information on rule of origin, existing competition, market conditions and price range on the market. The required specifications must comply with generally accepted market standards for similar type of supplies.

Bear in mind that the award criteria for supplies and works is price and tenderers might offer minimum requested quality in order to provide as lowest price as possible.

It is recommended to request performance guarantee for the procedures above 100.000 EUR.

In case the tender is divided into lots, a separate Technical Specifications must be prepared for each lot within the Tender Dossier. In principle, each lot results in a separate contract, which increases administrative workload. Normally, one lot is awarded to one tenderer; however, multiple lots can be concluded with the same tenderer in line with the evaluation results.

WORKS

Description of works should be sufficiently detailed in terms of procedures and expectations from the tenderer. The required specifications must comply with normal market standards for similar type of works. Bill of Quantities is the key part of the Tender documents, and it describes all details of the works to be implemented and supplies to be installed. Grant Beneficiary needs to prepare detailed description of the works prior to the tender procedure to avoid any potential non-delivery in the implementation phase. Design drawings are detailed graphic presentation of actual site situation and expected works. If some specific material needs to be built in, its specification should be drafted respecting the rule of avoiding mentioning the brand name described in the previous paragraph (SUPPLY).

### Instructions for the section of the document: 3. ADDITIONAL INFORMATION

ADMINISTRATIVE COMPLIANCE GRID:

Depending on the nature and subject of the contract, the Grant Beneficiary may request evidence documents in order to determine that a tenderer possesses necessary capacity for implementation of the contract (permits, licences, diplomas, brochures, catalogues, drafts, etc.). In such cases, the administrative compliance grid is included in the tender dossier in order to record the administrative compliance of each of the tenders. The administrative requirements will be checked within administrative check, which means that they must be formulated in a way that a simple yes/no check can be performed. Special attention should be paid in order to avoid confusing these administrative check requirements with inputs required within technical information that will be the subject of technical evaluation.

Some examples of administrative requirements:

  - A tenderer must be enrolled or registered in a relevant professional, legal or trade register, except when the economic operator is an international organisation.

  - For service contracts, the tenderer must hold the necessary authorisation proving that it is entitled to perform the contract in its country of establishment or be a member of a relevant professional organisation.

EVALUATION GRID:

The adequate criteria for the evaluation of tenders for service contracts shall be defined under section 3. Additional information of a document PART A – Information for the tenderers, in order to ensure the principles of transparency and equal treatment. A total of 100 points should be distributed among: Organization and methodology, required inputs and timeframe, according to their relevance for the quality of the service to be provided.

It is recommended to consult relevant PRAG templates and either use what is proposed in the template or make adequate maximum scores per each criterion. Evaluation grid structure and scoring must not be altered once the tender is launched.

In addition to PART A – Information for the tenders, a draft contract between the Grant Beneficiary and the tenderer is prepared and annexed. Please note that the price stated in the Article 2 is without VAT. Draft contract needs to provide information on the schedule of payments, if and when applicable. In case a pre-finance payment is necessary, Grant Beneficiary may request pre-financing guarantee, depending on the pre-financing value and risk assessed. For supply and works contracts, Grant Beneficiary may request performance guarantee, depending on the value of the contract, complexity and risk assessed. The duration of the contract must be indicated, in line with the template.

Please note that the duration of any secondary procurement contract must fall within the implementation period of the Grant Contract. Any cost incurred after the end of the Grant Contract implementation period will not be considered eligible.

  - Document: Part B – Format of offer to be provided by the tenderer

The offer must be submitted using the prescribed format. Any tenderer not using the prescribed form may be rejected by the Grant Beneficiary.

The tender must be submitted within the deadline, in line with technical requirements and using contact information provided in the Part A – Information for the tenderer (section Address and means for submission of the tenders).

  - Document Part C – Financial offer

This form is used only for service contracts. Financial offer must be submitted using Part C – Financial offer, placed in a separate envelope. There must not be any reference to the price in the Part B or any other document placed inside the envelope containing technical offer.

For supply and works tenders, financial offer is included in document Part B Technical and financial offer, of tender documentation.

### Step 4 – Tender launch

Related annexes: Annexes 5.2. and 5.3.

The tender launch begins with the invitation of selected tenderers and the dispatch of the tender dossier, prepared in line with the information obtained during the market research phase.

The invitation letter and tender dossier shall be sent by email, and Grant Beneficiaries must keep proof that the invitations were sent. Inviting potential tenderers must be properly documented - telephone invitations are not allowed.

The process must always respect the principles of transparency, proportionality, equal treatment, non-discrimination, and fair competition. Tenderers must submit their offers no later than the date and time specified in the document PART A - Information for the tenderer.

During the tendering period, Grant beneficiary, acting as the Contracting Authority, should provide clarifications to tenderers if requested. All clarifications must be distributed equally, at the same time and in the same form (e.g. by email) to all participants to ensure equal treatment.

Before the submission deadline, the Evaluation Committee should be appointed. Members must sign a Declaration of absence of conflict of interest and of confidentiality (Annex 5.3 point 06). While the appointment of the Evaluation Committee is not mandatory for the single tender procedure, it is highly recommended to ensure impartial and transparent assessment.

It is also recommended to launch the tender early in the project implementation, especially for local open or simplified procedures, to allow sufficient time for re-launch in case too few valid offers are received.

### Step 5 – Tender evaluation

Related annexes: Annexes 5.3.

Appointment of the Evaluation Committee is not obligatory for the Single Tender procedure, but it is highly recommended.

Nomination of the Evaluation Committee

Evaluation Committee should be appointed timely and formally by the Grant beneficiary, acting as the Contracting Authority for the procedure. This Committee shall comprise of a non-voting Chairperson, a non-voting Secretary and an odd number of voting members (minimum of three). At least one substitute member should be nominated. Observers may be nominated as well. CA/IBFM may decide to participate as observer (e.g. on the basis of the risk assessment).

The Evaluation Committee members should attend all meetings. Any absence must be recorded and explained in the Evaluation Report. All voting members of the Evaluation Committee have equal voting rights. The voting members must possess the necessary technical and administrative capacities. Persons authorized to sign contracts with awarded tenderer or appoint the Evaluation Committee on behalf of the Grant Beneficiary cannot be in the Evaluation Committee.

Any externally engaged staff for participation in Evaluation Committee due to specific expertise required, must be justified (relevant previous expertise and CV) and formalized.

Declaration for tender evaluation

All members of the Evaluation Committee and any observers must sign a Declaration of absence of conflict of interest and of confidentiality (see Annex 5.3 point 06). Any Evaluation Committee member or observer who has a potential conflict of interest due to a link with any tenderer must immediately withdraw from the Evaluation Committee. She/He will be excluded from participating further in the Evaluation Committee meetings and will be replaced. In this case evaluation process must be restarted. Any assessment by a voting member withdrawing from the Committee at whatever stage of the evaluation has to be disregarded.

No information about the examination, clarification, evaluation or decisions about the contract award can be disclosed before the contract signature. Any attempt by a tenderer to influence the process in any way (whether by initiating contact with members of the Evaluation Committee or otherwise) may result in the immediate exclusion of its tender from further consideration.

The tender offers should not leave the room/building in which the Committee meetings take place before the end of the evaluation process. They should be kept in a safe place during evaluation process.

Responsibilities of the Evaluation Committee Members

The Chairperson is responsible for coordinating the evaluation process in accordance with the procedures stipulated in this Manual and for ensuring its impartiality and transparency.

The Secretary of the Committee is responsible for carrying out all administrative tasks related to the evaluation process, preparation of Evaluation Report and supporting documents.

The voting members of the Evaluation Committee have collective responsibility for decisions taken by the Evaluation Committee.

### The Grant beneficiary should ensure to prepare evaluation reports for the tenders between 2.500 and 20.000 EUR. The template of the evaluation report is annexed to this procedure (Annexes 5.3.).

Evaluation process includes three phases: check of administrative compliance, technical, and financial evaluation. In case of service contracts when more than one tender is received, the envelope Part C – Financial offer must stay sealed until financial evaluation. The evaluation of such tender shall be performed by ranking offers according to scores awarded, in weighting technical quality against price on an 80/20 basis, as detailed in PRAG. If the tender is eliminated during administrative check or technical evaluation, the envelope containing Part C – Financial Offer must stay sealed forever.

If only one offer is received, no scoring will be applied but will be checked if the offer is administratively, technically and financially compliant with the criteria set by tender documentation.

    - Administrative compliance

During this phase, the Evaluation Committee confirms that formal requirements set in the Part A – Information for the tenderer (deadline, language, double envelope system…) are met, using yes/no check in Evaluation Report. Only administratively compliant offers are eligible for technical evaluation.

    - Technical evaluation

For supply and works contracts and for service contracts in case one offer is received, technical evaluation is performed using yes/no check in order to confirm that the offer meets minimum technical requirements set in Part A – Information for the tenderer. No scoring will be applied in this case.

For supply and works tenders, only technically compliant offers will be eligible for financial evaluation.

For service contracts in case more than one offer is received, each is evaluated and scored for the quality of organization and methodology, inputs and timeframe for implementation of activities, as presented in the part B – Tender submission form, Section 3 Technical offer. Only tenderers scored with minimum of 75 points are eligible for financial evaluation.

    - Financial evaluation

Financial evaluation implies verification that the price of the offer is within the available budget.

During the evaluation of tenders, the Evaluation Committee members use Annex 5.4. Procurement risk indicators. They must also ensure that the following steps are being implemented:

- receipt and registration of tenders (acknowledgement of receipt, numbering, safe keeping);

- tender opening using the opening checklist and preparation of Opening report,

- Administrative compliance using Administrative grid, including verification of signed statements and declarations signed and completeness of the tender submission forms,

- technical evaluation (for services – use evaluation grid, score ToR and CVs if requested; for supplies/works – yes/no compliance),

- financial evaluation (check arithmetical errors, comparing offers),

- completion of the Evaluation Report, reflecting all stages of evaluation, including reasons for rejection, scoring methodology, decisions and recommendations.

The Evaluation Report must be initialled on each page and signed by all members of the Evaluation Committee.

### Step 6 – Contract award

Related annexes: Annexes 5.3.

All tenderers will be informed of the results of the evaluation procedure in written simultaneously and individually.

The successful tenderer will be informed of the results of the evaluation procedure in written using Notification letter provided as in Annex 5.3. Tender evaluation documents – 09 “Contract award Notification letter” and proceeded with contract signature.

In cases when more than one offer was received, also the unsuccessful tenderers must be notified (using templates from Annex 5.3. Tender evaluation documents – folder 04 “Unsuccessful tenderers – Notification letters”).

Please see the draft letter for unsuccessful tenderers and the draft letter for second best tenderers for service contracts with more than one tender received (Annex 5.3. Tender evaluation documents – folder 04 “Unsuccessful tenderers – Notification letters”).

Where the contract cannot be concluded with the best ranked successful tenderer, the Contracting authority may award it to the following best tenderer.

Contracts for services/ supplies/ works will be concluded using the standardised format provided in Part A of single tender dossiers. The contract template must be filled in with information in line with tender dossier and tender offer (implementation period, contract amount, payment schedule adjusted to financial offer, relevant annexes such as technical offer, FIF, LEF, etc.)

Contracts are considered to take effect from the date of signature of the last signatory. Contracts or contract addenda cannot be awarded retroactively (i.e. after the end of the execution period) under any circumstances.

Once the contract has been signed the Grant beneficiary is responsible for drafting the award notice without delay. Contract award notice will be published on the Grant beneficiary website, in the language of the procedure. It is recommended that the Contract award notice is published within 7 days after the date of contract signature.

Complaints to the Grant beneficiary

Without prejudice to other remedies, where a tenderer believes he has been adversely affected by an error or irregularity allegedly committed as part of a selection or procurement procedure, or that the procedure was vitiated by any maladministration, he may file a complaint to the Grant beneficiary.

The complaint shall be substantiated, and its sole subject shall not be to obtain a second evaluation for no reason other than the complainant disagrees with the final award decision.

The Grant beneficiary will endeavour to investigate the complaint and respond within maximum 30 calendar days. Alternatively, if the candidate, tenderer is not satisfied with the answer received, he may also file ordinary actions, provided the conditions stipulated in the national legislation are met.

Where the European Commission is not the contracting authority, the action shall be launched in accordance with the conditions and deadlines fixed by the national legislation of the Grant Beneficiary.

### Step 7 – Contract implementation

Related annexes: Annexes 3

### Grant Beneficiaries are responsible for ensuring proper and transparent implementation of awarded contracts. In practice, this means:

- close monitoring of contract implementation;

- requiring reporting by the Contractor, where applicable;

- using Timesheets for service contracts, where applicable;

- using Provisional/Final Acceptance Certificates for supply and works contracts;

- ensuring that costs related to poor quality outputs or deliveries are not accepted as eligible;

- verifying compliance with communication and visibility rules;

- applying the VAT exemption procedure.

A complete and verifiable audit trail must be maintained. All correspondence with tenderers and contractors (e.g. emails, letters, notifications) must be kept on record. Communication should always be in writing to ensure transparency and accountability.

All changes in the content of the awarded performance must be documented.

Evidence that the successful tenderer delivered, at the tendered cost, exactly what was in the original specification and the Grant beneficiary’s provisional and/or final acceptance certificate(s) / report approved by the Grant beneficiary’s, will be provided for verification to the CA/IBFM/Control body and programme audit. The format of provisional and/or final acceptance certificate(s) is provided as Annex 3.7. of this Manual while the format of the “Report on services provided” shall be agreed between the two signatory parties. For works the reports will be submitted according to national legislation.

If during the implementation of the contract, Grant beneficiary identifies a situation that can be associated with the conflict of interest, it has the obligation to inform the JTS and CFCU and take the necessary measures in order to remedy the situation.

Acceptance certificates:

For supplies and works, the official or other servant technically competent shall draw up a final acceptance certificate, or a provisional and a final acceptance certificate, in the following situations:

- A. in case the Performance Guarantee is not required: a Final acceptance certificate will be issued.

The supplies shall be taken over by the Grant Beneficiary when they have been delivered,  installed, tested  and found compliant with the technical specifications of the supply contract, or have been commissioned as the case may be, and a certificate of final acceptance has been issued or is deemed to have been issued. In addition, the Contractor shall demonstrate that the obligations set out in the Communication and Visibility Manual have been complied in line with the article 9.9. of the General Conditions.

- B. in case the Performance Guarantee is required: a Provisional acceptance certificate and  Final acceptance certificate will be issued.

The supplies shall be taken over by the Grant Beneficiary when they have been delivered, installed, tested  and found compliant with the technical specifications of the supply contract, or have been commissioned as the case may be, and a certificate of provisional acceptance has been issued or is deemed to have been issued. Upon expiry of the warranty period, or where there is more than one such period, upon expiry of the latest period, and when all defects or damage have been recmedied, the Project Manager shall issue the Contractor a final acceptance certificate and a copy thereof to the Grant Beneficiary, stating the date on which the Contractor completed its obligations under the contract to the Project Manager's satisfaction. The final acceptance certificate shall be issued by the Project Manager within 30 days after the expiration of the warranty period or as soon as any repairs ordered have been completed to the satisfaction of the Project Manager.

- SIMPLIFIED PROCEDURE

The simplified procedure is applied for contracts above EUR 20,000 and below the thresholds for local or international open procedures. Procurement under this procedure may take up to three months, so this must be taken into account when planning the implementation of other project activities.

### Simplified procedures should follow the procurement steps described below:

### Step 1 – Market research

Before launching the procedure, the Grant beneficiary conducts market research to collect information about current prices, rule of origin, technical characteristics, and potential suppliers or service providers. Based on this research, at least three potential tenderers must be identified. The choice of invited tenderers must be justified using objective criteria (see Annex 5.2, example documents  01a and 01b, Market Research and Justification for Tender Invitation). The list of invited entities must be included in the Tender Dossier.

### Step 2 – Preparation of the Tender Dossier

The Grant Beneficiary prepares a complete Tender Dossier, which must include all necessary information to allow tenderers to prepare their offers properly. It is recommended to use the relevant PRAG templates, depending on the type of procurement procedure (SERVICE, SUPPLY, WORKS), in particular the following applicable templates:

SERVICE – recommended PRAG templates to be used:

- Declaration of honour on exclusion and selection criteria

- Letter of invitation to tender

- Instructions to tenderers and contract notice

- Draft contract agreemen,: main conditions and special conditions with annexes:

  - General conditions for service contracts (Annex I)

  - Terms of reference (Annex II)

  - Organisation and methodology (Annex III)

  - List of profiles of key experts (Annex IV)

  - Budget (Annex V)

Forms and other relevant documents:

- Tender submission form

- Applicable Identification form (natural person/private law body/public law body)

- Pre-financing guarantee template, where applicable (Annex VI)

- Expenditure verification: terms of reference and report of factual findings, where applicable (Annex VII)

For further information:

- Administrative compliance grid

- Evaluation grid

For full details of the tendering procedure and applicable templates, please see the Practical Guide and its annexes, which may be downloaded from the following website: https://wikis.ec.europa.eu/display/ExactExternalWiki/ePRAG

SUPPLY – recommended PRAG templates to be used:

- Declaration of honour on exclusion and selection criteria

- Letter of invitation to tender

- Instructions to tenderers and contract notice

- Draft contract agreement, main conditions and special conditions with annexes:

  - General conditions for supply contracts (Annex I)

  - Technical specifications (ANNEX II)

  - Technical offer (ANNEX III)

  - Model financial offer (ANNEX IV)

  - Peformance guarantee, where applicable (Annex V)

  - Pre-financing guarantee, where applicable (Annex VI)

Forms and other supporting documents

- Tender submission form

- Applicable Identification form (natural person/private law body/public law body)

- Provisional and Final Acceptance Certificate (in line with contract conditions)

For further information:

- Administrative compliance grid

- Evaluation grid

For full details of the tendering procedures and applicable templates, please see the Practical Guide and its annexes, which may be downloaded from the following website: https://wikis.ec.europa.eu/display/ExactExternalWiki/ePRAG

WORKS – recommended PRAG templates to be used:

VOLUME 1:

- Declaration of honour on exclusion and selection criteria

- Letter of invitation to tender

- Instructions to tenderers and contract notice

- Tender form for a works contract

- Tender guarantee form, where applicable

- Technical offer questionnaire

- Technical offer form 4.1 - General information about the tenderer

- Technical offer form 4.2 - Organisation chart

- Technical offer form 4.3 - Power of attorney

- Technical offer form 4.4 - Financial statement

- Technical offer form 4.6 - Technical qualifications

- Applicable Identification form (natural person/private law body)

- Minutes of site visit / clarification meeting (if organised)

- Administrative compliance grid

- Evaluation grid

VOLUME 2:

- Draft contract agreement, main conditions and special conditions with annexes:

  - General conditions for works contracts

  - Performance guarantee, where applicable

  - Pre-financing payment guarantee, where applicable

VOLUME 3:

- Technical specifications

VOLUME 4:

- Financial offer

- Financial offer lump sum contracts and/or unit price contracts (as applicable)

- Bill of Quantities (for unit price contracts), where applicable

VOLUME 5:

- Design documents, including drawings

For full details of the tendering procedures and applicable templates, please see the practical guide and its annexes, which may be downloaded from the following website: https://wikis.ec.europa.eu/display/ExactExternalWiki/ePRAG

The Tender Dossier must clearly define eligibility, selection and award criteria, contractual obligations, delivery terms, guarantees, payment conditions, and any other requirements. For service contracts, the ToR should specify required expertise; for supplies and works, technical specifications must comply with normal market standards and rule of origin.

For more information on selection criteria,please see section 2.6.11 Selection and award criteria in PRAG 2025.

SELECTION CRITERIA:

Selection criteria - SERVICE / SUPPLY / WORKS

Grant Beneficiaries shall draw up clear and non-discriminatory selection criteria for the purpose of assessing that the tenderer has enough financial, economic, technical and professional capacity to implement the tasks of the contract. The chosen criteria shall be proportionate, reflecting market conditions (making sure that invited tenderers can meet selection criteria) and may not go beyond the scope of the contract.

For the economic and financial capacity, the reference period may be no more than the last 3 years for which accounts have been closed.

For the financial capacity, it shall be considered that the average annual turnover tenderers are required to have shall not exceed the size of the estimated contract value.

For professional and technical capacity, the tenderer should demonstrate the experience in contracts of similar size, value and complexity within a reference period not exceeding 3-5 years from the submission deadline (e.g. providing a reference to the activities implemented in the last 3 years for services and supplies, and to the activities implemented in the last 5 years for works).

For professional capacity, requirements should be proportionate, and the tenderer shall not be asked to provide more staff than necessary for proper implementation of the contract.

For the technical capacity, it shall be considered that the minimum value of references (technical capacity) the tenderers are required to have (one or a sum of more references) shall not exceed the estimated contract value.

If necessary, Grant Beneficiaries may define some other selection criteria in single tender. In that case, tenderers are obliged to respect and fulfil those criteria.

Concerning supporting documents/proofs from the tenderers, it should be indicated which supporting documents/proofs and when they are required.

SELECTION CRITERIA:

To ensure fair competition and equal treatment of all candidates, the following examples illustrate restrictive or disproportionate selection criteria that should be avoided:

- Requesting disproportionate requirements (e.g. annual turnover, number of staff, or number of previous projects) in comparison with the estimated contract value;

- Using imprecise or subjective terms such as “sufficient”, “major”, or “relevant”, which are too ambiguous and open to interpretation;

- Requesting that a specific percentage of staff work in certain fields, which may create disproportionate requirements and be discriminatory for companies of different sizes or organisational structures;

- Requiring technical experience limited only to EU-funded projects, as this may be considered discriminatory and unnecessarily restrictive;

- Requiring prior experience in the partner country, unless duly justified by the specific nature of the contract;

- Requesting overly prescriptive or narrow technical experience that effectively limits eligibility to one or very few companies.

### Step 3 – Tender launch

The Grant beneficiary sends a letter of invitation to tender together with the Tender Dossier to at least three justified candidates. Invitations shall be sent by e-mail, but proof of dispatch must be kept. Tenderers must be given at least 30 days from the date of dispatch to submit their tenders.

### Step 4 – Appointment of the Evaluation Committee

The Grant beneficiary must appoint the Evaluation Committee members having necessary technical and administrative expertise. The Evaluation Committee must have an odd number of members. All members must sign a Declaration of Impartiality and Confidentiality. A Chairperson and Secretary are not obligatory but recommended if staff capacity allows.

### Step 5 – Receipt and registration of tenders

All tenders must be registered with the date and time of receipt, kept unopened and stored securely until the official opening session.

### Step 6 – Opening and evaluation of tenders

### n of tenders

Tenders are opened and evaluated by the Evaluation Committee. The process includes:

- Administrative compliance check using the administrative compliance grid,

- Technical evaluation using the criteria and scoring system set out in the Tender Dossier,

- Financial evaluation, including verification of arithmetic accuracy of the offers.

The award criteria are:

- Best value for money (quality-price ratio) for service contracts,

- Lowest price among technically compliant offers for supply and works contracts.

If only one administratively and technically valid offer is received, the contract may still be awarded, provided that the award criteria are met.

### Step 7 – Evaluation Report

### n of tenders

The Evaluation Committee prepares an Evaluation Report, recording all stages of the evaluation, discussions, decisions and recommendations. The report must be accompanied by the administrative and technical grids, copies of tenders, and other relevant documentation. The Evaluation Report is confidential and for official use only.

### Step 8 – Notifications and contract signature

### n of tenders

The successful tenderer is notified, and the validity of its offer is automatically extended for 60 days. At the same time, all unsuccessful tenderers who submitted offers are informed about the outcome. Afterwards, the contract is prepared and signed.

For all tender procedures above 20.000 EUR, the annexes elaborated in the practical guide on contract procedures for European Union external action (PRAG) will be applied. The version of PRAG to be used is the latest version available at the date of the launching of the corresponding Call for Proposals / Guidelines for applicants – PRAG 2025 valid from 20/01/2025.

PraG documents are available at:

https://wikis.ec.europa.eu/display/ExactExternalWiki/ePRAG

PraG Annexes are available at:

https://wikis.ec.europa.eu/display/ExactExternalWiki/Annexes