Annex 5.6. Single Tender Procedure: Step-by-step checklist

## Step 1 - Procurement Planning

- ☐ Prepare Procurement Plan (PP) - Annex 1.8

- ☐ Ensure consistency with Description of Action (Annex I) and Grant Budget (Annex III)

- ☐ Submit PP to JTS (for consultation) and to CFCU (for approval) within the first month of implementation

- ☐ If needed, implement JTS/CFCU comments

## Step 2 - Market Research

- ☐ Conduct market research / market assessment (min. 3 references)

- ☐ Prepare market research table - Annex 5.1 (Market research for supply contract – example)

- ☐ Prepare Market Research and Justification for Tender Invitation - Annex 5.2

- ☐ Attach copies of pro-forma offers / online price references / supporting documentation

## Step 3 - Tender Preparation

- ☐ Ensure all preparatory team members sign Declaration of Objectivity and Confidentiality – Annex 5.1 (05)

- ☐ Draft Single Tender Dossier – Annex 5.2, including:

- ☐ Part A - Information for Tenderers

- ☐ Part B - Technical Offer Template

- ☐ Part C - Financial Offer Template (for services only)

- ☐ Consult JTS before launching the procedure

## Step 4 - Tender Launch

- ☐ Based on market assessment, send Invitation Letter + Tender Dossier by email/post (keep proof of sending)

- ☐ Provide clarifications equally to all tenderers (in writing, record kept)

- ☐ Appoint Evaluation Committee - Decision on appointment of Evaluation Committee– Annex 5.3 (05)

- ☐ Collect signed Declarations of Impartiality and Confidentiality – Annex 5.3 (06)

## Step 5 - Tender Evaluation

- ☐ Register received tenders - Register of Tenders received - Annex 5.3 (07)

- ☐ Issue Acknowledgement of Receipt - Annex 5.3 (08)

- ☐ Conduct Tender Opening Session using:

- ☐ Opening Checklist & Opening Report - Annex 5.3

- ☐ Ensure all envelopes opened simultaneously, sealed and initialled

- ☐ For services: keep financial offer sealed

- ☐ For supplies/works: announce financial offers

- ☐ Use Administrative Compliance Grid (from Tender Dossier - Part A)

- ☐ Verify signed declarations and completeness of tender submission forms, supporting documents

- ☐ Evaluate the tenders using Evaluation Grid (from Tender Dossier - Part A)

- ☐ For services: evaluate Organisation & Methodology, Inputs, Time frame

- ☐ For supplies/works: evaluate YES/NO technical compliance

- ☐ Verify supporting evidence (CVs, certificates, etc.)

- ☐ Check arithmetic accuracy (record in Evaluation Report)

- ☐ For services: apply 80/20 quality-price ratio (Annex 5.3)

- ☐ For supplies/works: compare compliant offers per lot

- ☐ Complete Evaluation Report (each page initialled, last page signed by all EvC members) and Negotiation Report – Annex 5.3

- ☐ Attach administrative and technical grids, scoring sheets, clarifications

## Step 6 - Contract Award

- ☐ Prepare Contract Dossier: Contract Agreement (Annex 5.2), Technical & Financial Offers, LEF/FIF if applicable

- ☐ Send Contract Award Notification Letter - Annex 5.3 (“09 Contract award Notification letter”)

- ☐ Send Unsuccessful Tenderer Notification Letters - Annex 5.3 (folder “Unsuccessful tenderers”)

- ☐ Prepare Cancellation Notice, if applicable - Annex 5.3

- ☐ Publish Contract Award Notice (within 7 days after signature)

## Step 7 - Contract Implementation

- ☐ Monitor contract implementation and correspondence

- ☐ Request contractor’s reports / Timesheets (services) - Annex 3

- ☐ Use Provisional / Final Acceptance Certificates (supplies/works) - Annex 3.7

- ☐ Check quality of deliverables; reject ineligible costs for poor outputs

- ☐ Verify compliance with Communication and Visibility Rules

- ☐ Apply VAT exemption procedure

- ☐ Maintain complete audit trail – all records and communications archived